## Instructions
CHANGE SCORECARD TEMPLATE
Change can be squishy. And yet, measuring change is a key success factor for any change for several reasons. Measuring success makes it easier to justify investment in proper change management in the first place. Also, measuring the progress of change makes it easier to evaluate and adjust various change interventions if they are not making the desired impact to the degree anticipated. Each change is different and the scorecard metrics need to be customized for the specific change being implemented. Some changes, like IT implementation, are easier than others, like a culture change. However, all change can be measured. The leadership spitball conversation is a good place to start for ideas on what success looks like for the leader(s). Then you can figure out how to quantitatively measures those factors for success. Below are some ideas for the four catergories included in the change scorecard.
THE FOUR CATEGORIES OF MEASURES
Financial - These metrics should be a way to show that the change team is maximizing any budget they received and utilizing it appropriately. This also helps to measure the true cost of change. Typically, measures in this category include budget utilization (you don't want to go over budget because that is poor management and if you are underutilizing, that might show poor, or slow, roll out of initiatives. There may also be other financial metrics you can include, depending on the change. If, for instance, your change includes a consolidation of functions, you might have a direct cost savings as a result of the change that could be included in this category as well.
Change Process - When you quantitatively measure your change process against your plan, you show leadership how productive the change team is being. Do not underestimate the importance of showing that productivity; it is key to percieved value. Metrics in this category will be based on your change strategy and the interventions you have. Metrics in this category might include things like communications metrics (number of each type delivered, open rate, click through rate, pulse surveys to the workforce, and pule surveys to the change network on effectiveness of messaging); training metrics (number of each type delivered, participant scores for delivery, content, and relevance); adherence to change plan (time, scope, and budget); and any percentage of workforce metrics specific to the change. For instance, if you need the entire workforce to switch to using a different IT tool, or sign acknowledgement of a new policy, etc., a percent complete metric will be useful.
Stakeholders - In this section, you want to measure how your change interventions are impacting the key stakeholders they are intending to impact. This, most likely, will include the workforce as a whole. There may be specific subsystems of the workforce whose adoption needs to be measured separately (for instance, supervisors, or the marketing team). Those measures would go hear as well. The metric I almost always include is the self-assessment of employees along the behavior-based change continuum I create (download the EVOLVE Change Customization Worksheet, if you haven't already, to learn more). Any other specific behaviors that can be tracked can be included here as well. For instance, if you are moving towards a more dispersed workforce, metrics such as % of paper files digitized or average days of telework per week might be meaningful metrics. Behaviors are observable and trackable and are therefor great metrics to include in this section.
Indirect Impact - These measures are typically the more traditional metrics used to measure projects that are not directly impacted by the change interventions but the desire to improve these metrics might have been the impetus for the change in the first place. If the change in question is a consolidation of functions and a joining of cultures for a merger and acquisition, metrics in this section might be employee retention (or reduction of voluntary attrition), employee engagement, employee net promoter score, customer retention, customer net promoter score, broader productivity measures, and sales/revenue, growth, and profit metrics. The change initiative itself may not have a 1 for 1 relationship with these metrics, but it is still important to track these aspects because these metrics hit at the root cause as to why the change program was invested in to begin with.
After defining metrics/measures for each category, follow the following steps: 1. Use the metrics to fill in the Scorecard tab. Your metrics will typically align with groups of Objectives, so you can fill the specific metrics/measures into Column C, grouped by common objectives, in Column B. 2. Define targets for each measure and record it in Column D. 3. Use the scorecard to get leadership buy-in, making adjustments as needed. 4. Track the measures at least quarterly and provide an update to leadership using the dashboard and scorecard tabs.

## Dashboard
Change Name:
Quarter (click to see status):
|  |  | Target | Actual |  |  | Target | Actual
|  | Measure 1 | 12 | 4 |  | Measure 7 | 12 | 2
|  | Measure 2 | 12 | 4 |  | Measure 8 | 12 | 2
|  | Measure 3 | 12 | 4 |  | Measure 9 | 12 | 6
|  | Measure 4 | 12 | 3 |  | Measure 10 | 12 | 2
|  | Measure 5 | 12 | 4
|  | Measure 6 | 12 | 3
| Narrative for Quarter 1 goes here to show up on the dashboard page for senior leadership. Keep it brief and high level, sharing key risks, things you need from them, and key successes. |  |  |  | Q1
|  |  | Target | Actual |  |  | Target | Actual
|  | Measure 11 | 12 | 1 |  | Measure 19 | 12 | 4
|  | Measure 12 | 12 | 3 |  | Measure 20 | 12 | 4
|  | Measure 13 | 12 | 4 |  | Measure 21 | 12 | 4
|  | Measure 14 | 12 | 4 |  | Measure 22 | 12 | 4
|  | Measure 15 | 12 | 3 |  | Measure 23 | 12 | 2
|  | Measure 16 | 12 | 2 |  | Measure 24 | 12 | 1
| Q1 | Measure 17 | 12 | 2 | Q1 | Measure 25 | 12 | 4
|  | Measure 18 | 12 | 4
Change Process
Indirect Impact
Q1
Q2
Q3
Q4
Financial
Stakeholders
Q1
Overall Status in
3.000
3.286
Q1
Overall Status in
Q1
Overall Status in
3.667
Overall Status in
Q1
2.875

## Scorecard
Perspective | Objective | Measure | Annual Target | Q1 |  | Q2 |  | Q3 |  | Q4 |  | Initiatives | Calculation - Do Not Adjust
|  |  |  | Actual | Status | Actual | Status | Actual | Status | Actual | Status |  | Overall Status | Speedometer | Overall Chart
Financial | Objective 1 | Measure 1 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  |  | Financial |  | Pointer
|  | Measure 2 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  | 3.6667 | Red | 0 | 29.1667 | 1
| Objective 2 | Measure 3 | 12 | 4 | 33.33% | 6 | 50% | 8 | 66.67% | 11 | 91.67% |  |  | Yellow | 0 | 2
|  | Measure 4 | 12 | 3 | 25% | 5 | 41.67% | 7 | 58.33% | 10 | 83.33% |  |  | Green | 100 | 170.8333
| Objective 3 | Measure 5 | 12 | 4 | 33.33% | 6 | 50% | 8 | 66.67% | 12 | 100% |  |  | Reminder | 100 |  | Q1
|  | Measure 6 | 12 | 3 | 25% | 5 | 41.67% | 7 | 58.33% | 12 | 100% |  |  | Red | 0
Stakeholders | Objective 4 | Measure 7 | 12 | 2 | 16.67% | 4 | 33.33% | 6 | 50% | 12 | 100% |  | 3 | Yellow | 0 | 23.5
|  | Measure 8 | 12 | 2 | 16.67% | 4 | 33.33% | 6 | 50% | 12 | 100% |  |  | Green | 100 | 2
| Objective 5 | Measure 9 | 12 | 6 | 50% | 8 | 66.67% | 10 | 83.33% | 11 | 91.67% |  |  | Reminder | 100 | 176.5
|  | Measure 10 | 12 | 2 | 16.67% | 4 | 33.33% | 6 | 50% | 10 | 83.33% |  |  | Red | 0
Change Process | Objective 6 | Measure 11 | 12 | 1 | 8.333% | 3 | 25% | 5 | 41.67% | 9 | 75% |  |  | Yellow | 100
|  | Measure 12 | 12 | 3 | 25% | 5 | 41.67% | 7 | 58.33% | 8 | 66.67% |  | 2.875 | Green | 0 | 22.4375
| Objective 7 | Measure 13 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  |  | Reminder | 100 | 2
|  | Measure 14 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  |  | Red | 0 | 177.5625
| Objective 8 | Measure 15 | 12 | 3 | 25% | 5 | 41.67% | 7 | 58.33% | 10 | 83.33% |  |  | Yellow | 0
|  | Measure 16 | 12 | 2 | 16.67% | 4 | 33.33% | 6 | 50% | 10 | 83.33% |  |  | Green | 100
| Objective 9 | Measure 17 | 12 | 2 | 16.67% | 4 | 33.33% | 6 | 50% | 12 | 100% |  |  | Reminder | 100
|  | Measure 18 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 11 | 91.67% |  |  | Total
Indirect Impacts | Objective 10 | Measure 19 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  | 3.2857 |  |  | 25.9286
|  | Measure 20 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  |  |  |  | 2
| Objective 11 | Measure 21 | 12 | 4 | 33.33% | 6 | 50% | 9 | 75% | 12 | 100% |  |  |  |  | 174.0714
|  | Measure 22 | 12 | 4 | 33.33% | 6 | 50% | 8 | 66.67% | 11 | 91.67%
| Objective 12 | Measure 23 | 12 | 2 | 16.67% | 4 | 33.33% | 6 | 50% | 12 | 100%
|  | Measure 24 | 12 | 1 | 8.333% | 3 | 25% | 6 | 50% | 12 | 100%
|  | Measure 25 | 12 | 4 | 33.33% | 6 | 50% | 7 | 58.33% | 10 | 83.33%
[13 empty] | Red | 0
[13 empty] | Yellow | 0
[13 empty] | Green | 25
[13 empty] | Reminder | 0.01
[13 empty] | Red | 0
[13 empty] | Yellow | 0
[13 empty] | Green | 25
[13 empty] | Reminder | 0.01
[13 empty] | Red | 0
[13 empty] | Yellow | 25
[13 empty] | Green | 0
[13 empty] | Reminder | 0.01
[13 empty] | Red | 0
[13 empty] | Yellow | 0
[13 empty] | Green | 25
[13 empty] | Reminder | 0.01
[13 empty] | Total | 100.03
Note on C1: Mary: You want these measures to be quanitative. They can be process related (e.g. number of Town Hall meetings held) or can be more traditional key performance indicators based on the change you are measuring. You want things you can measure at least quarterly, if not more frequently. Things also should be directly impacted by the change. Don't forget about including risk mitigation metrics. For instance, you may have a productivity metric you anticipate going down. You can include that productivity metric and show how the change management efforts kept the productivity metric from dropping as low as it could have.
Note on M1: Mary: It's all about alignment. Here, you can list the initiatives and how they "map" to the various metrics here. This is especially helpful if your initiatives require funding or other resources. It is also helpful to course correct if you are not getting the impact you need.

## Narrative
Narrative for the Dashboard - Remember the audience is senior executives
| Q1 | Q2 | Q3 | Q4
Financial | Narrative for Quarter 1 goes here to show up on the dashboard page for senior leadership. Keep it brief and high level, sharing key risks, things you need from them, and key successes. | Q2 | Q3 | Q4
Stakeholder | Q1 | Q2 | Q3 | Q4
Change Process | Q1 | Q2 | Q3 | Q4
Indirect Impact | Q1 | Q2 | Q3 | Q4